## dev points
Ressource | Priority | Estimated Hours | Estimated delivery Date | Department | Description | FIT/GAP | GAP Category | Technica Priority | Solution Design Prepared | Solution Design Approved | Infosys GAP recommendation
Abdullah | 2 | 76 | 2025-11-19 | Sales | Inside Change stage in sales process we need several mandatory fields - Competitor & Buyer/ contact & condition to move within different stages. Ability to navigate stages backward. | GAP | Requirement | High | 02092025 - Technica - Sales - Change in Sales Process | Approved
Lea | 1 | 4 | 2025-11-04 | Proc&Sourcing | Add previous purchase price on PO line. | GAP | Requirement | High | 05092025 - Technica - Purchasing - Details of the purchase order line | Approved
Lea | 2 | 8 | 2025-11-13 | Project Mngt | Ability of PM to check the status of PO (invoiced & paid by finance) vs Status of Project invoice status (invoiced & paid by customer) | GAP | Requirement | High | 26092025 - Technica - Purchase Invoices vs Project Invoices | Approved
Lea | 1 | 16 | 2025-11-06 | Proc&Sourcing | Adding Requested Delivery date & vendor delivery date + payment terms to RFQ comparison /RFQ comparison: Payment terms and delivery date are needed. | GAP | Adding Fields | High | 03092025 - Technica - Sales - RFQ comparison | Approved
Lea | 1 | 20 | 2025-11-10 | Proc&Sourcing | Workflow by project manager | GAP | Workflow | High | 03092025 - Technica - Purchasing - PO workflow by PM | Approved | Recommended
Wassim | 1 | 48 | 2025-11-12 | Project Mngt | Planned POs to be filtered by project ID | GAP | Grid | High | 19082025 - Technica - Project Management addition of project ID | Approved | Recommended
|  |  | 2025-11-12 | Project Mngt | POs generated from master plan can’t be tracked from list to which assembly they are ordered; retreive the project ID on planned PO, Purchase orders and production orders | GAP | Requirement | High | 19082025 - Technica - Project Management addition of project ID | Approved | Recommended
|  |  | 2025-11-12 | Proc&Sourcing | Planned order should reflect activity ID on item requirement from the project. | GAP | Requirement | High | 19082025 - Technica - Project Management addition of project ID | Approved | Recommended
|  |  | 2025-11-12 | Inventory Mngt | adding brand on item level; dragging it to PO form, SO form, production order, planned orders | GAP | Requirement | High | 19082025 - Technica - Project Management addition of project ID - Copy Appendix B | Approved
Abdullah | 1 | 6 | 2025-11-04 | Inventory Mngt | Critical on hand inventory report: to view items below min qty. We need same report but to compare with available physical, not physical inventory. | GAP | View | High | 23092025 - Technica - Critical on-hand inventory | Approved | Recommended
Wassim | 2 | 8 | 2025-11-13 | Production | The “All Production Orders” list should show Qty started, qty pending and qty finished for each production order. | GAP | Requirement | High | 25092025 - Technica - Production Overview | Approved
Wassim | 3 | 6 | 2025-11-21 | Spare Parts | Price calculation to be checked (Item cost + markup + margin) on sales quotation level; Change contribution rates on quotation | GAP | Requirement | High | 05092025 - Technica - Sales - Item unit price calculation | Approved | Recommended
Wassim | 3 | 10 | 2025-11-25 | Spare Parts | SPL list generation to be customized by Infosys based on Cedric excel; Add item selling price in the list For every item in the stock a category should be added (critical, recommended, none, consumables) -> SPL is the list of items used in the project (all but type 'none') and will be sent to the client. | GAP | View | High | 13102025 - Technica - Critical recommended consumables spare parts | Approved | Recommended
Wassim | 3 | 16 | 2025-11-27 | Spare Parts | Disable (Release, estimate and start) of a prod. order or a PO if payment is not received when a prepayment is requested on Sales order; Prepayment condition: if not received cannot proceed with purchases and production | GAP | Requirement | High | 26082025 - Technica - Disable (Release, estimate and start) of a prod. order or a PO if payment is not received when a prepayment is requested on Sales order; | Approved
Lea | 2 | 10 | 2025-11-17 | Project Mngt | PAID checkbox on the on-account invoices | GAP | Grid | High | 26092025 - Technica - Finance PAID checkbox on the on-account invoices | Approved
Lea | 2 | 20 | 2025-11-20 | Project Mngt | Customer statement generation filtering by posting profiles "Shipment" or "Prepayment" | GAP | Requirement | High | 26092025 - Technica - Finance Projects number sequence and statement appendix b | Approved | Recommended
Lea | 2 |  |  | Project Mngt | Having 2 different sequence numbers for the invoice journal generated from the project proposal invoices. | GAP | Requirement | High | 26092025 - Technica - Finance Projects number sequence and statement | Approved
Lea | 1 | 10 | 2025-11-12 | Proc&Sourcing | Planned purchase orders firming should result in draft purchase orders that need to be submitted to workflow | GAP | Requirement | High | 02102025 - Technica - Purchasing - PO workflow from MRP | Approved
Abdullah | 2 | 5 | 2025-11-20 | Sales | A main contact should be selected from the opportunity contacts and auto-added to the contact on the main opportunity page | GAP | Requirement | High | 13102025 - Technica - Sales - Selection of contact in opportunity | Approved
Lea | 2 | 5 | 2025-11-21 | Project Mngt | Transfer to project should be disabled after project creation | GAP | Requirement | High | 13102025 - Technica - Transfer to project from quotations | Approved
Lea | 2 | 14 | 2025-11-25 | Project Mngt | Control sum of on-account transactions based on the quotation amount | GAP | Requirement | High | 20102025 - Technica - Control on account transactions amount | Approved
Abdullah | 2 | 10 | 2025-11-21 | Inventory Mngt | Add project id to the arrival overview form | GAP | Requirement | High | 20102025 - Technica - Arrival overview project ID | Approved | Recommended
Wassim | 2 | 40 | 2025-11-20 | Production | When the actual time spent passes the estimated time, the user needs to specify a reason in real time before being able to complete the job & a notification to be sent to team leader | GAP | Requirement + Notification | High | 07102025 - Technica - Production floor execution | Approved
Lea | 2 | 10 |  | Spare Parts | Delivery date in sales/project quotation to be managed by weeks. Once confirmed: confirmed date + number of days or weeks to be reflected on sales order
Lea | 2 |  |  | Spare Parts | in sales /project quotation header to have field - [delivery after nbr of weeks]

## Sheet3
Department | Solution Design | Description | Original Estimated Hours | Modification | Final development hours
Sales | 02092025 - Technica - Sales - Change in Sales Process | Inside Change stage in sales process we need several mandatory fields - Competitor & Buyer/ contact & condition to move within different stages. Ability to navigate stages backward. | 76 |  | 76
Proc&Sourcing | 05092025 - Technica - Purchasing - Details of the purchase order line | Add previous purchase price on PO line. | 4 |  | 4
Project Mngt | 26092025 - Technica - Purchase Invoices vs Project Invoices | Ability of PM to check the status of PO (invoiced & paid by finance) vs Status of Project invoice status (invoiced & paid by customer) | 8 |  | 8
Proc&Sourcing | 03092025 - Technica - Sales - RFQ comparison | Adding Requested Delivery date & vendor delivery date + payment terms to RFQ comparison /RFQ comparison: Payment terms and delivery date are needed. | 16 |  | 16
Proc&Sourcing | 03092025 - Technica - Purchasing - PO workflow by PM | Workflow by project manager | 20 |  | 20
Project Mngt | 19082025 - Technica - Project Management addition of project ID - Copy Appendix E | filter master plan per Sales order, or ability to copy sales order lines items and save it to master line with link to SO nbr ; Filter master plan by SO similar to project | 56 | -8 | 48
Project Mngt | 19082025 - Technica - Project Management addition of project ID | Planned POs to be filtered by project ID
Project Mngt | 19082025 - Technica - Project Management addition of project ID | POs generated from master plan can’t be tracked from list to which assembly they are ordered; retreive the project ID on planned PO, Purchase orders and production orders
Project Mngt | 19082025 - Technica - Project Management addition of project ID | Planned order should reflect activity ID on item requirement from the project.
Project Mngt | 19082025 - Technica - Project Management addition of project ID - Copy Appendix B | adding brand on item level; dragging it to PO form, SO form, production order, planned orders
Inventory Mngt | 23092025 - Technica - Critical on-hand inventory | Critical on hand inventory report: to view items below min qty. We need same report but to compare with available physical, not physical inventory. | 6 |  | 6
Production | 25092025 - Technica - Production Overview | The “All Production Orders” list should show Qty started, qty pending and qty finished for each production order. | 8 |  | 8
Spare Parts | 05092025 - Technica - Sales - Item unit price calculation | Price calculation to be checked (Item cost + markup + margin) on sales quotation level; | 6 |  | 6
Change contribution rates on quotation
Spare Parts | 13102025 - Technica - Critical recommended consumables spare parts | SPL list generation to be customized by Infosys based on Cedric excel; Add item selling price in the list | 10 |  | 10
For every item in the stock a category should be added (critical, recommended, none, consumables) -> SPL is the list of items used in the project (all but type 'none') and will be sent to the client.
Spare Parts | 26082025 - Technica - Disable (Release, estimate and start) of a prod. order or a PO if payment is not received when a prepayment is requested on Sales order; | Disable (Release, estimate and start) of a prod. order or a PO if payment is not received when a prepayment is requested on Sales order; | 16 | Pending Technica Decision | 0
Prepayment condition: if not received cannot proceed with purchases and production
Project Mngt | 26092025 - Technica - Finance PAID checkbox on the on-account invoices | PAID checkbox on the on-account invoices | 10 |  | 10
Project Mngt | 26092025 - Technica - Finance Projects number sequence and statement appendix b | Customer statement generation filtering by posting profiles "Shipment" or "Prepayment" | 20 |  | 20
Project Mngt | 26092025 - Technica - Finance Projects number sequence and statement | Having 2 different sequence numbers for the invoice journal generated from the project proposal invoices.
Proc&Sourcing | 02102025 - Technica - Purchasing - PO workflow from MRP | Planned purchase orders firming should result in draft purchase orders that need to be submitted to workflow | 10 |  | 10
Sales | 13102025 - Technica - Sales - Selection of contact in opportunity | A main contact should be selected from the opportunity contacts and auto-added to the contact on the main opportunity page | 5 |  | 5
Project Mngt | 13102025 - Technica - Transfer to project from quotations | Transfer to project should be disabled after project creation | 5 |  | 5
Project Mngt | 20102025 - Technica - Control on account transactions amount | Control sum of on-account transactions based on the quotation amount | 14 |  | 14
Inventory Mngt | 20102025 - Technica - Arrival overview project ID | Add project id to the arrival overview form | 10 |  | 10
Production | 07102025 - Technica - Production floor execution | When the actual time spent passes the estimated time, the user needs to specify a reason in real time before being able to complete the job & a notification to be sent to team leader | 40 |  | 40
Spare Parts | 26082025 - Technica - Spare parts Quotation to be managed by weeks | Delivery date in sales/project quotation to be managed by weeks. Once confirmed: confirmed date + number of days or weeks to be reflected on sales order |  | 10 | 10
Spare Parts | 26082025 - Technica - Spare parts Quotation to be managed by weeks | in sales /project quotation header to have field - [delivery after nbr of weeks]
|  |  | 340 |  | 326

## Sheet1
90 | 11.25 | 76
4 | 0.5 | 4
8 | 1 | 8
16 | 2 | 16
20 | 2.5 | 20
56 | 7 | 56
6 | 0.75 | 6
8 | 1 | 8
8 | 1 | 8
10 | 1.25 | 10
16 | 2 | -16
12 | 1.5 | 12
12 | 1.5 | 12
12 | 1.5 | 6
10 | 1.25 | 10
5 | 0.625 | 5
5 | 0.625 | 5
14 | 1.75 | 14
10 | 1.25 | 10
40 | 5 | 40

## dev points (2)
Estimated Hours | Department | Solution Design Prepared | Description | FIT/GAP | GAP Category | Technica Priority | Solution Design Approved | Infosys GAP recommendation
76 | Sales | 02092025 - Technica - Sales - Change in Sales Process | Inside Change stage in sales process we need several mandatory fields - Competitor & Buyer/ contact & condition to move within different stages. Ability to navigate stages backward. | GAP | Requirement | High | Approved
4 | Proc&Sourcing | 05092025 - Technica - Purchasing - Details of the purchase order line | Add previous purchase price on PO line. | GAP | Requirement | High | Approved
8 | Project Mngt | 26092025 - Technica - Purchase Invoices vs Project Invoices | Ability of PM to check the status of PO (invoiced & paid by finance) vs Status of Project invoice status (invoiced & paid by customer) | GAP | Requirement | High | Approved
16 | Proc&Sourcing | 03092025 - Technica - Sales - RFQ comparison | Adding Requested Delivery date & vendor delivery date + payment terms to RFQ comparison /RFQ comparison: Payment terms and delivery date are needed. | GAP | Adding Fields | High | Approved
20 | Proc&Sourcing | 03092025 - Technica - Purchasing - PO workflow by PM | Workflow by project manager | GAP | Workflow | High | Approved | Recommended
48 | Project Mngt | 19082025 - Technica - Project Management addition of project ID | Planned POs to be filtered by project ID | GAP | Grid | High | Approved | Recommended
| Project Mngt | 19082025 - Technica - Project Management addition of project ID | POs generated from master plan can’t be tracked from list to which assembly they are ordered; retreive the project ID on planned PO, Purchase orders and production orders | GAP | Requirement | High | Approved | Recommended
| Proc&Sourcing | 19082025 - Technica - Project Management addition of project ID | Planned order should reflect activity ID on item requirement from the project. | GAP | Requirement | High | Approved | Recommended
| Inventory Mngt | 19082025 - Technica - Project Management addition of project ID - Copy Appendix B | adding brand on item level; dragging it to PO form, SO form, production order, planned orders | GAP | Requirement | High | Approved
6 | Inventory Mngt | 23092025 - Technica - Critical on-hand inventory | Critical on hand inventory report: to view items below min qty. We need same report but to compare with available physical, not physical inventory. | GAP | View | High | Approved | Recommended
8 | Production | 25092025 - Technica - Production Overview | The “All Production Orders” list should show Qty started, qty pending and qty finished for each production order. | GAP | Requirement | High | Approved
6 | Spare Parts | 05092025 - Technica - Sales - Item unit price calculation | Price calculation to be checked (Item cost + markup + margin) on sales quotation level; Change contribution rates on quotation | GAP | Requirement | High | Approved | Recommended
10 | Spare Parts | 13102025 - Technica - Critical recommended consumables spare parts | SPL list generation to be customized by Infosys based on Cedric excel; Add item selling price in the list For every item in the stock a category should be added (critical, recommended, none, consumables) -> SPL is the list of items used in the project (all but type 'none') and will be sent to the client. | GAP | View | High | Approved | Recommended
16 | Spare Parts | 26082025 - Technica - Disable (Release, estimate and start) of a prod. order or a PO if payment is not received when a prepayment is requested on Sales order; | Disable (Release, estimate and start) of a prod. order or a PO if payment is not received when a prepayment is requested on Sales order; Prepayment condition: if not received cannot proceed with purchases and production | GAP | Requirement | High | Approved
10 | Project Mngt | 26092025 - Technica - Finance PAID checkbox on the on-account invoices | PAID checkbox on the on-account invoices | GAP | Grid | High | Approved
20 | Project Mngt | 26092025 - Technica - Finance Projects number sequence and statement appendix b | Customer statement generation filtering by posting profiles "Shipment" or "Prepayment" | GAP | Requirement | High | Approved | Recommended
| Project Mngt | 26092025 - Technica - Finance Projects number sequence and statement | Having 2 different sequence numbers for the invoice journal generated from the project proposal invoices. | GAP | Requirement | High | Approved
10 | Proc&Sourcing | 02102025 - Technica - Purchasing - PO workflow from MRP | Planned purchase orders firming should result in draft purchase orders that need to be submitted to workflow | GAP | Requirement | High | Approved
5 | Sales | 13102025 - Technica - Sales - Selection of contact in opportunity | A main contact should be selected from the opportunity contacts and auto-added to the contact on the main opportunity page | GAP | Requirement | High | Approved
5 | Project Mngt | 13102025 - Technica - Transfer to project from quotations | Transfer to project should be disabled after project creation | GAP | Requirement | High | Approved
14 | Project Mngt | 20102025 - Technica - Control on account transactions amount | Control sum of on-account transactions based on the quotation amount | GAP | Requirement | High | Approved
10 | Inventory Mngt | 20102025 - Technica - Arrival overview project ID | Add project id to the arrival overview form | GAP | Requirement | High | Approved | Recommended
40 | Production | 07102025 - Technica - Production floor execution | When the actual time spent passes the estimated time, the user needs to specify a reason in real time before being able to complete the job & a notification to be sent to team leader | GAP | Requirement + Notification | High | Approved
10 | Spare Parts | 26082025 - Technica - Spare parts Quotation to be managed by weeks | Delivery date in sales/project quotation to be managed by weeks. Once confirmed: confirmed date + number of days or weeks to be reflected on sales order
| Spare Parts | 26082025 - Technica - Spare parts Quotation to be managed by weeks | in sales /project quotation header to have field - [delivery after nbr of weeks]